## Sheet1
id | carry_forward_id | budget_id | rev_no | entry_on_progress_flag | carry_forward_price | end_date | order_complete_flag | carry_forward_reason | carry_forward_year_from | carry_forward_year_to | settlement_no | lost_flag | entry_datetime | entry_operator | update_datetime | update_operator
1 | 1 | 17721 | 0 | 0 | 117080000 |  |  |  | 2021 |  |  | 1 | 2022-03-25 07:49 | shin-ito
2 | 1 | 17721 | 1 | 0 | 117080000 | 2023-03-31 | 0 | 埋設物調査結果判明後着手 | 2021 |  |  | 1 | 2022-03-25 07:55 | shin-ito | 2022-03-25 07:55 | shin-ito
3 | 2 | 18693 | 0 | 0 | 28292000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:06 | s-owada
4 | 3 | 21569 | 0 | 0 | 83019000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:07 | s-owada
5 | 4 | 16823 | 0 | 0 | 39500000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:07 | s-owada
6 | 5 | 21466 | 0 | 0 | 7000000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:08 | s-owada
7 | 6 | 21877 | 0 | 0 | 10546000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:08 | s-owada
8 | 7 | 21292 | 0 | 0 | 270000000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:09 | s-owada
9 | 8 | 21394 | 0 | 0 | 7500000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:09 | s-owada
10 | 9 | 21462 | 0 | 0 | 35000000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:09 | s-owada
11 | 10 | 21464 | 0 | 0 | 7000000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:10 | s-owada
12 | 11 | 21921 | 0 | 0 | 2037000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:10 | s-owada
13 | 12 | 21920 | 0 | 0 | 6395000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:10 | s-owada
14 | 13 | 21670 | 0 | 0 | 7200000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:11 | n-otowa
15 | 3 | 21569 | 1 | 0 | 28510000 | 2022-05-31 | 1 | ケーブル新規受注停止による工事・試運転の遅延 | 2021 |  |  | 1 | 2022-03-29 05:14 | s-owada | 2022-03-29 05:14 | s-owada
16 | 2 | 18693 | 1 | 0 | 28292000 | 2022-10-31 | 0 | 2021定修で検査及び補修を行い更新は2022定修とした | 2021 |  |  | 1 | 2022-03-29 05:16 | s-owada | 2022-03-29 05:16 | s-owada
17 | 4 | 16823 | 1 | 0 | 38240810 | 2022-12-27 | 0 | 当初仕様で予算超過した為、2021定修で内部確認し仕様再検討した | 2021 |  |  | 1 | 2022-03-29 05:25 | s-owada | 2022-03-29 05:50 | s-owada
18 | 13 | 21670 | 1 | 0 | 215000 | 2022-06-30 | 1 | 製品品質に問題があり、原課より問題解決までストップが掛かり工事実施待ち状態となっている。（発注済み） | 2021 |  |  | 1 | 2022-03-29 05:26 | n-otowa | 2022-03-29 05:26 | n-otowa
19 | 5 | 21466 | 1 | 0 | 960000 | 2022-07-31 | 1 | 機器納期5ケ月により繰越 | 2021 |  |  | 1 | 2022-03-29 05:26 | s-owada | 2022-03-29 05:26 | s-owada
20 | 14 | 20012 | 0 | 0 | 860020000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:27 | n-otowa
21 | 6 | 21877 | 1 | 0 | 10546000 | 2022-07-31 | 0 | 機器納期5ヶ月により繰越 | 2021 |  |  | 1 | 2022-03-29 05:28 | s-owada | 2022-03-29 05:50 | s-owada
22 | 14 | 20012 | 1 | 0 | 474900000 | 2022-08-31 | 0 | 当初の予定通り、2022年8月に完工予定。 | 2021 |  |  | 1 | 2022-03-29 05:28 | n-otowa | 2022-03-29 05:28 | n-otowa
23 | 7 | 21292 | 1 | 0 | 7085760 | 2022-09-30 | 1 | 部品納期8ヶ月により繰越 | 2021 |  |  | 1 | 2022-03-29 05:29 | s-owada | 2022-03-29 05:29 | s-owada
24 | 10 | 21464 | 1 | 0 | 3680000 | 2022-11-30 | 1 | 部品納期5ヵ月、8ヶ月により繰越 | 2021 |  |  | 1 | 2022-03-29 05:31 | s-owada | 2022-03-29 05:31 | s-owada
25 | 8 | 21394 | 1 | 0 | 443000 | 2022-06-30 | 1 | 整備期間実働75日により繰越 | 2021 |  |  | 1 | 2022-03-29 05:32 | s-owada | 2022-03-29 05:32 | s-owada
26 | 15 | 21741 | 0 | 0 | 195800000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:33 | n-otowa
27 | 9 | 21462 | 1 | 0 | 365000 | 2022-05-31 | 1 | 部品納期5ヵ月により繰越 | 2021 |  |  | 1 | 2022-03-29 05:34 | s-owada | 2022-03-29 05:34 | s-owada
28 | 12 | 21920 | 1 | 0 | 6395000 | 2022-06-30 | 0 | 年度末発生の追加工事 | 2021 |  |  | 1 | 2022-03-29 05:36 | s-owada | 2022-03-29 05:36 | s-owada
29 | 11 | 21921 | 1 | 0 | 2037000 | 2022-05-31 | 0 | 年度末発生の追加工事 | 2021 |  |  | 1 | 2022-03-29 05:36 | s-owada | 2022-03-29 05:36 | s-owada
30 | 15 | 21741 | 1 | 0 | 48400000 | 2022-07-31 | 1 | 当初予定通り7月末完工予定。 ※発注完了状態は「発注完了」としているが、今後の工事で地中障害物が発見、除去が必要な場合は追加予算申請予定。 | 2021 |  |  | 1 | 2022-03-29 05:37 | n-otowa | 2022-03-29 05:37 | n-otowa
31 | 16 | 20824 | 0 | 0 | 100000000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:45 | n-otowa
32 | 16 | 20824 | 1 | 0 | 55402000 | 2023-03-31 | 0 | 予定工事の一部を除き完了（予定より安価に完了） 引き続き耐震10か年計画に沿って対応する。 | 2021 |  |  | 1 | 2022-03-29 05:46 | n-otowa | 2022-03-29 05:53 | n-otowa
33 | 17 | 18304 | 0 | 0 | 389523000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:54 | s-owada
34 | 18 | 16463 | 0 | 0 | 145461000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:54 | s-owada
35 | 19 | 16513 | 0 | 0 | 155000000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:55 | s-owada
36 | 20 | 19732 | 0 | 0 | 32300000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:55 | s-owada
37 | 21 | 21522 | 0 | 0 | 107409000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:56 | s-owada
38 | 22 | 21816 | 0 | 0 | 9842000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:56 | s-owada
39 | 23 | 21865 | 0 | 0 | 2286000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:57 | s-owada
40 | 24 | 21873 | 0 | 0 | 1672000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:57 | n-otowa
41 | 25 | 21896 | 0 | 0 | 19397000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:57 | s-owada
42 | 24 | 21873 | 1 | 0 | 1635000 | 2022-05-31 | 1 | 当初予定通り2022年7月完工予定。 | 2021 |  |  | 1 | 2022-03-29 05:58 | n-otowa | 2022-03-29 05:58 | n-otowa
43 | 26 | 21358 | 0 | 0 | 5000000 |  |  |  | 2021 |  |  | 1 | 2022-03-29 05:58 | s-owada
44 | 17 | 18304 | 1 | 0 | 388263000 | 2023-02-28 | 0 | 当初の計画通り2023年完工予定 | 2021 |  |  | 1 | 2022-03-29 06:00 | s-owada | 2022-03-29 06:00 | s-owada
45 | 19 | 16513 | 1 | 0 | 48996000 | 2022-07-31 | 0 | 基礎設計変更に伴う工期延長 | 2021 |  |  | 1 | 2022-03-29 06:02 | s-owada | 2022-03-29 06:02 | s-owada
46 | 18 | 16463 | 1 | 0 | 69157000 | 2022-06-30 | 0 | アスベスト含有が確認され工期延長 | 2021 |  |  | 1 | 2022-03-29 06:03 | s-owada | 2022-03-29 06:03 | s-owada
47 | 26 | 21358 | 1 | 0 | 2400000 | 2022-04-30 | 1 | 電気配線の整理が必要となり工期延長 | 2021 |  |  | 1 | 2022-03-29 06:05 | s-owada | 2022-03-29 06:05 | s-owada
48 | 20 | 19732 | 1 | 0 | 2204000 | 2022-04-30 | 1 | 施工業者の確保が出来ず工期を延長 | 2021 |  |  | 1 | 2022-03-29 06:08 | s-owada | 2022-03-29 06:08 | s-owada
49 | 21 | 21522 | 1 | 0 | 46544900 | 2022-04-30 | 0 | ケーブル新規受注停止による納期延長により繰越 | 2021 |  |  | 1 | 2022-03-29 06:09 | s-owada | 2022-03-29 06:09 | s-owada
50 | 22 | 21816 | 1 | 0 | 9842000 | 2022-06-30 | 0 | 製作納期の関係で当初より繰越予定 | 2021 |  |  | 1 | 2022-03-29 06:11 | s-owada | 2022-03-29 06:11 | s-owada
51 | 23 | 21865 | 1 | 0 | 1186000 | 2022-07-31 | 1 | 機器納期4.5ヵ月により繰越 | 2021 |  |  | 1 | 2022-03-29 06:12 | s-owada | 2022-03-29 06:12 | s-owada
52 | 25 | 21896 | 1 | 0 | 8447000 | 2022-06-30 | 0 | 定修で外したファンのFRP/L納期により繰越 | 2021 |  |  | 1 | 2022-03-29 06:14 | s-owada | 2022-03-29 06:14 | s-owada
53 | 27 | 21262 | 0 | 0 | 15000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 05:37 | s-owada
54 | 27 | 21262 | 1 | 0 | 586000 | 2022-05-31 | 1 | 機器納期１ヵ年による繰越 | 2021 |  |  | 1 | 2022-03-30 05:39 | s-owada | 2022-03-30 05:39 | s-owada
55 | 28 | 21166 | 0 | 0 | 10000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 08:24 | s-owada
56 | 28 | 21166 | 1 | 0 | 612000 | 2022-04-30 | 1 | 納入されたポンプが仕様と違い、電気工事及び試運転が出来ず繰越 | 2021 |  |  | 1 | 2022-03-30 08:25 | s-owada | 2022-03-30 08:25 | s-owada
57 | 29 | 19995 | 0 | 0 | 13000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 09:08 | n-otowa
58 | 29 | 19995 | 1 | 0 | 6150000 | 2022-05-31 | 1 | 急遽試掘作業が発生し、構造計算期間がズレ込んだ為、繰り越しが必要となった。 | 2021 |  |  | 1 | 2022-03-30 09:11 | n-otowa | 2022-03-30 09:11 | n-otowa
59 | 30 | 18352 | 0 | 0 | 131000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 09:46 | n-otowa
60 | 31 | 21890 | 0 | 0 | 12800000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 09:46 | n-otowa
61 | 32 | 21791 | 0 | 0 | 40722000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 09:53 | n-otowa
62 | 33 | 21695 | 0 | 0 | 5760000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 09:54 | n-otowa
63 | 34 | 20630 | 0 | 0 | 20000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 09:55 | n-otowa
64 | 35 | 20169 | 0 | 0 | 28300000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 09:55 | n-otowa
65 | 36 | 21276 | 0 | 0 | 17000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 10:02 | shin-ito
66 | 36 | 21276 | 1 | 0 | 4550000 | 2022-09-30 | 1 | ライニング業者の施工ミス | 2021 |  |  | 1 | 2022-03-30 10:06 | shin-ito | 2022-03-30 10:06 | shin-ito
67 | 37 | 21902 | 0 | 0 | 2900000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 10:25 | shin-ito
68 | 37 | 21902 | 1 | 0 | 2900000 | 2022-05-31 | 1 | 当初計画どおり | 2021 |  |  | 1 | 2022-03-30 10:27 | shin-ito | 2022-03-30 10:29 | shin-ito
69 | 38 | 21383 | 0 | 0 | 3000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 10:36 | shin-ito
70 | 38 | 21383 | 1 | 0 | 3000000 | 2022-10-31 | 0 | 総合電気室更新工事と工期を合わせるため | 2021 |  |  | 1 | 2022-03-30 10:38 | shin-ito | 2022-03-30 10:38 | shin-ito
71 | 39 | 21401 | 0 | 0 | 7647000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 10:39 | shin-ito
72 | 39 | 21401 | 1 | 0 | 3798000 | 2023-03-31 | 0 | 総合電気室更新工事と工期を合わせるため | 2021 |  |  | 1 | 2022-03-30 10:41 | shin-ito | 2022-03-30 10:41 | shin-ito
73 | 40 | 21384 | 0 | 0 | 6000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 10:42 | shin-ito
74 | 40 | 21384 | 1 | 0 | 1963000 | 2022-09-30 | 0 | 設計作業が未完のため工事仕様未定 | 2021 |  |  | 1 | 2022-03-30 10:44 | shin-ito | 2022-03-30 10:44 | shin-ito
75 | 41 | 21755 | 0 | 0 | 6000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 10:45 | shin-ito
76 | 41 | 21755 | 1 | 0 | 3090000 | 2022-10-31 | 0 | 工期が定修期間に限定されるため | 2021 |  |  | 1 | 2022-03-30 10:47 | shin-ito | 2022-03-30 10:47 | shin-ito
77 | 42 | 20357 | 0 | 0 | 11000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 11:13 | shin-ito
78 | 42 | 20357 | 1 | 0 | 950000 | 2022-05-30 | 1 | D-367の影響による生産都合 | 2021 |  |  | 1 | 2022-03-30 11:16 | shin-ito | 2022-03-30 11:16 | shin-ito
79 | 43 | 20347 | 0 | 0 | 10000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 11:17 | shin-ito
80 | 43 | 20347 | 1 | 0 | 1280000 | 2022-05-30 | 1 | D-367の影響による生産都合 | 2021 |  |  | 1 | 2022-03-30 11:19 | shin-ito | 2022-03-30 11:19 | shin-ito
81 | 14 | 20012 | 2 | 0 | 414970000 | 2022-08-31 | 0 | 当初の予定通り、2022年8月に完工予定。 | 2021 |  |  | 1 | 2022-03-30 23:47 | n-otowa | 2022-03-30 23:47 | n-otowa
82 | 44 | 21793 | 0 | 0 | 12670000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 23:51 | shin-ito
83 | 44 | 21793 | 1 | 0 | 11538000 | 2022-12-31 | 0 | 定修に工期変更 | 2021 |  |  | 1 | 2022-03-30 23:53 | shin-ito | 2022-03-30 23:53 | shin-ito
84 | 30 | 18352 | 1 | 0 | 8750000 | 2022-04-28 | 1 | 監視カメラ(付属機器含む)の長納期化及びケーブル配線材の長納期化により繰越しとなる。 | 2021 |  |  | 1 | 2022-03-30 23:53 | n-otowa | 2022-03-31 00:11 | n-otowa
85 | 45 | 21412 | 0 | 0 | 70000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 23:54 | shin-ito
86 | 14 | 20012 | 3 | 0 | 425250000 | 2022-08-31 | 0 | 当初の予定通り、2022年8月に完工予定。 | 2021 |  |  | 1 | 2022-03-30 23:55 | n-otowa | 2022-03-30 23:55 | n-otowa
87 | 45 | 21412 | 1 | 0 | 9509000 | 2022-06-30 | 1 | 仕様追加 | 2021 |  |  | 1 | 2022-03-30 23:55 | shin-ito | 2022-03-30 23:55 | shin-ito
88 | 46 | 20654 | 0 | 0 | 32000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 23:57 | shin-ito
89 | 46 | 20654 | 1 | 0 | 15600000 | 2022-05-31 | 1 | 原課指示で工期変更 | 2021 |  |  | 1 | 2022-03-30 23:58 | shin-ito | 2022-03-30 23:58 | shin-ito
90 | 47 | 20648 | 0 | 0 | 5000000 |  |  |  | 2021 |  |  | 1 | 2022-03-30 23:59 | shin-ito
91 | 47 | 20648 | 1 | 0 | 960000 | 2022-05-31 | 1 | 分解後軸部の不良が発覚した | 2021 |  |  | 1 | 2022-03-31 00:01 | shin-ito | 2022-03-31 00:01 | shin-ito
92 | 48 | 20728 | 0 | 0 | 12000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 00:02 | shin-ito
93 | 48 | 20728 | 1 | 0 | 480000 | 2022-05-31 | 1 | 部品納期が04月になったため | 2021 |  |  | 1 | 2022-03-31 00:03 | shin-ito | 2022-03-31 00:03 | shin-ito
94 | 49 | 21899 | 0 | 0 | 3170000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 00:06 | shin-ito
95 | 49 | 21899 | 1 | 0 | 3170000 | 2022-12-31 | 0 | 着手が遅くポンプ未納のため未着工 | 2021 |  |  | 1 | 2022-03-31 00:11 | shin-ito | 2022-03-31 00:11 | shin-ito
96 | 31 | 21890 | 1 | 0 | 12800000 | 2022-04-28 | 1 | 機器納入が発注後７カ月となっており、現時点未発注につき納入は７月以降となり繰り越しとなる。 | 2021 |  |  | 1 | 2022-03-31 00:12 | n-otowa | 2022-03-31 00:12 | n-otowa
97 | 34 | 20630 | 1 | 0 | 19791000 | 2023-03-31 | 0 | OPCサーバーからPIサーバーに接続する為のOPCサーバーアップグレードが2022年1月中旬まで伸びてしまい繰越となった。 | 2021 |  |  | 1 | 2022-03-31 00:20 | n-otowa | 2022-03-31 00:20 | n-otowa
98 | 32 | 21791 | 1 | 0 | 1600000 | 2022-05-31 | 1 | A工場静置建屋東側ﾊﾟｲﾌﾟﾗｯｸ補強関係で追加工事が発生した為、繰越とする。 | 2021 |  |  | 1 | 2022-03-31 00:24 | n-otowa | 2022-03-31 00:24 | n-otowa
99 | 33 | 21695 | 1 | 0 | 2900000 | 2022-06-30 | 0 | 次年度も引き続きシステム開発を行う為。 | 2021 |  |  | 1 | 2022-03-31 00:27 | n-otowa | 2022-03-31 00:33 | n-otowa
100 | 50 | 20254 | 0 | 0 | 30000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 00:29 | shin-ito
101 | 50 | 20254 | 1 | 0 | 30000000 | 2022-05-31 | 0 | 生産都合により工事延期 | 2021 |  |  | 1 | 2022-03-31 00:31 | shin-ito | 2022-03-31 00:31 | shin-ito
102 | 51 | 21176 | 0 | 0 | 5550000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 00:32 | shin-ito
103 | 51 | 21176 | 1 | 0 | 5250000 | 2022-12-30 | 0 | 詳細仕様検討中 | 2021 |  |  | 1 | 2022-03-31 00:33 | shin-ito | 2022-03-31 00:33 | shin-ito
104 | 35 | 20169 | 1 | 0 | 25000000 | 2022-05-31 | 0 | 電気部品遅延による消防検査未受検、消防検査後に実施される付帯設備の改造（仕様書発行済み）がある為、繰越とする。※完工予定月は５月末としているが未だ納期情報入らず。 | 2021 |  |  | 1 | 2022-03-31 00:39 | n-otowa | 2022-03-31 08:41 | n-otowa
105 | 42 | 20357 | 2 | 0 | 4690000 | 2022-07-31 | 1 | D-367の影響による生産都合 | 2021 |  |  | 1 | 2022-03-31 01:54 | shin-ito | 2022-03-31 01:58 | shin-ito
106 | 52 | 20267 | 0 | 0 | 16000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 02:05 | shin-ito
107 | 52 | 20267 | 1 | 0 | 16000000 | 2022-07-31 | 0 | メーカー指導員がコロナ感染し、試運転が延期になったため | 2021 |  |  | 1 | 2022-03-31 02:07 | shin-ito | 2022-03-31 02:07 | shin-ito
108 | 53 | 20268 | 0 | 0 | 15000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 02:08 | shin-ito
109 | 53 | 20268 | 1 | 0 | 14310000 | 2022-09-30 | 0 | 屋根カバー工法実施前に構造計算を行い健全性を確認した。 然しながらNGとなり建屋補強が必要となったため、追加予算申請予定である。 | 2021 |  |  | 1 | 2022-03-31 02:14 | shin-ito | 2022-03-31 02:14 | shin-ito
110 | 54 | 20435 | 0 | 0 | 2500000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 02:27 | shin-ito
111 | 54 | 20435 | 1 | 0 | 6490000 | 2022-10-31 | 0 | 部品(メカシール)が長納期であったため | 2021 |  |  | 1 | 2022-03-31 02:29 | shin-ito | 2022-03-31 02:29 | shin-ito
112 | 55 | 20720 | 0 | 0 | 65600000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 02:46 | shin-ito
113 | 55 | 20720 | 1 | 0 | 62890000 | 2022-08-31 | 0 | コンプレッサー納期遅延および工事見積遅延のため | 2021 |  |  | 1 | 2022-03-31 02:49 | shin-ito | 2022-03-31 02:49 | shin-ito
114 | 56 | 18003 | 0 | 0 | 8000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 02:51 | shin-ito
115 | 56 | 18003 | 1 | 0 | 8060000 | 2022-12-30 | 0 | 新規蒸気ヘッダー図面作成に必要な現地調査、熱応力解析に時間を要するため | 2021 |  |  | 1 | 2022-03-31 02:54 | shin-ito | 2022-03-31 02:54 | shin-ito
116 | 57 | 20734 | 0 | 0 | 44000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 05:12 | shin-ito
117 | 57 | 20734 | 1 | 0 | 25082000 | 2022-05-31 | 0 | 基礎撤去工事が発生した | 2021 |  |  | 1 | 2022-03-31 05:13 | shin-ito | 2022-03-31 05:13 | shin-ito
118 | 58 | 21911 | 0 | 0 | 1650000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 05:16 | shin-ito
119 | 58 | 21911 | 1 | 0 | 2625000 | 2022-05-31 | 0 | フレキホース追加購入および追加工事発生 | 2021 |  |  | 1 | 2022-03-31 05:19 | shin-ito | 2022-03-31 05:19 | shin-ito
120 | 59 | 19869 | 0 | 0 | 75730000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 05:26 | shin-ito
121 | 59 | 19869 | 1 | 0 | 10499000 | 2022-08-31 | 0 | 材料長納期およびMM-1行蒸気配管の改造に時間を要するため | 2021 |  |  | 1 | 2022-03-31 05:29 | shin-ito | 2022-03-31 05:29 | shin-ito
122 | 60 | 20612 | 0 | 0 | 12000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 06:12 | shin-ito
123 | 60 | 20612 | 1 | 0 | 6000000 | 2022-04-30 | 1 | 足場撤去が期間内に完工しなかったため | 2021 |  |  | 1 | 2022-03-31 06:15 | shin-ito | 2022-03-31 06:15 | shin-ito
124 | 61 | 21667 | 0 | 0 | 1927000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 06:17 | shin-ito
125 | 62 | 21417 | 0 | 0 | 6000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 06:20 | shin-ito
126 | 63 | 21927 | 0 | 0 | 27000000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 06:24 | shin-ito
127 | 61 | 21667 | 1 | 0 | 1900000 | 2022-09-30 | 1 | 長納期のため | 2021 |  |  | 1 | 2022-03-31 06:26 | shin-ito | 2022-03-31 06:26 | shin-ito
128 | 62 | 21417 | 1 | 0 | 2380000 | 2022-06-30 | 0 | 1321YY641工事が完了後に着工可能となるため | 2021 |  |  | 1 | 2022-03-31 06:34 | shin-ito | 2022-03-31 06:34 | shin-ito
129 | 63 | 21927 | 1 | 0 | 27000000 | 2022-07-31 | 0 | 工期に時間を要するため | 2021 |  |  | 1 | 2022-03-31 06:36 | shin-ito | 2022-03-31 06:36 | shin-ito
130 | 64 | 21917 | 0 | 0 | 5260000 |  |  |  | 2021 |  |  | 1 | 2022-03-31 08:11 | n-otowa
131 | 64 | 21917 | 1 | 0 | 4710000 | 2022-09-30 | 0 | 当初計画通りの9月末完工予定。 | 2021 |  |  | 1 | 2022-03-31 08:18 | n-otowa | 2022-03-31 08:18 | n-otowa
132 | 16 | 20824 | 2 | 0 | 55402000 | 2023-03-31 | 0 | 予定工事の一部を除き完了（予定より安価に完了） 引き続き耐震10か年計画に沿って対応する。 | 2021 |  |  | 1 | 2022-03-31 08:37 | n-otowa | 2022-03-31 08:37 | n-otowa
133 | 64 | 21917 | 2 | 0 | 4710000 | 2022-09-30 | 0 | 当初計画通りの9月末完工予定。 | 2021 |  |  | 1 | 2022-03-31 08:39 | n-otowa | 2022-03-31 08:39 | n-otowa
134 | 43 | 20347 | 2 | 0 | 1260000 | 2022-05-30 | 1 | D-367の影響による生産都合 | 2021 |  |  | 1 | 2022-03-31 23:05 | n-otowa | 2022-03-31 23:05 | n-otowa
135 | 57 | 20734 | 2 | 0 | 43782000 | 2022-05-31 | 0 | 基礎撤去工事が発生した | 2021 |  |  | 1 | 2022-03-31 23:09 | n-otowa | 2022-03-31 23:09 | n-otowa
136 | 59 | 19869 | 2 | 0 | 17999000 | 2022-08-31 | 0 | 材料長納期およびMM-1行蒸気配管の改造に時間を要するため | 2021 |  |  | 1 | 2022-03-31 23:10 | n-otowa | 2022-03-31 23:10 | n-otowa
137 | 44 | 21793 | 2 | 0 | 18530000 | 2022-12-31 | 0 | 定修に工期変更 | 2021 |  |  | 1 | 2022-03-31 23:16 | n-otowa | 2022-03-31 23:16 | n-otowa
138 | 44 | 21793 | 3 | 0 | 18530000 | 2022-12-31 | 0 | 定修に工期変更 ※3/31現在 追加予算申請中分の￥6,722,000を加えた繰越額を記入している。 | 2021 |  |  | 1 | 2022-03-31 23:23 | n-otowa | 2022-03-31 23:23 | n-otowa
139 | 1 | 17721 | 2 | 0 | 113330000 | 2023-03-31 | 0 | 埋設物調査結果判明後着手 | 2021 |  |  | 1 | 2022-03-31 23:36 | n-otowa | 2022-03-31 23:36 | n-otowa
140 | 65 | 21270 | 0 | 0 | 2000000 |  |  |  | 2021 |  |  | 1 | 2022-04-01 00:07 | shin-ito
141 | 65 | 21270 | 1 | 0 | 478000 | 2022-06-30 | 1 | 納期遅延 | 2021 |  |  | 1 | 2022-04-01 00:08 | shin-ito | 2022-04-01 00:08 | shin-ito
142 | 44 | 21793 | 4 | 0 | 18260000 | 2022-12-31 | 0 | 定修に工期変更(仕様追加実施時期） 継続前提でA号稟議決裁済み | 2021 |  |  | 1 | 2022-04-01 05:46 | ke-katsurayama | 2022-05-10 05:18 | m-katsurayama
143 | 15 | 21741 | 2 | 0 | 50600000 | 2022-07-31 | 1 | 当初予定通り7月末完工予定。 ※発注完了状態は「発注完了」としているが、今後の工事で地中障害物が発見、除去が必要な場合は追加予算申請予定。 | 2021 |  |  | 1 | 2022-04-01 07:40 | n-otowa | 2022-04-01 07:40 | n-otowa
144 | 30 | 18352 | 2 | 0 | 5700000 | 2022-04-28 | 1 | 監視カメラ(付属機器含む)の長納期化及びケーブル配線材の長納期化により繰越しとなる。 | 2021 |  |  | 1 | 2022-04-01 07:48 | n-otowa | 2022-04-01 07:48 | n-otowa
145 | 30 | 18352 | 3 | 0 | 5700000 | 2022-04-28 | 1 | ケーブル配線材の長納期化により繰越しとなる。 | 2021 |  |  | 1 | 2022-04-01 07:50 | n-otowa | 2022-04-01 07:50 | n-otowa
146 | 31 | 21890 | 2 | 0 | 10200000 | 2022-04-28 | 1 | 機器納入が発注後７カ月となっており、現時点未発注につき納入は７月以降となり繰り越しとなる。 | 2021 |  |  | 1 | 2022-04-01 09:18 | n-otowa | 2022-04-01 09:18 | n-otowa
147 | 66 | 19661 | 0 | 0 | 22000000 |  |  |  | 2021 |  |  | 1 | 2022-04-05 00:28 | n-otowa
148 | 66 | 19661 | 1 | 0 | 0 | 2023-03-31 | 1 | 繰越額はゼロであるが入帳不可の為、予算のみ繰越とする。 （入庫上の手続き問題） | 2021 |  |  | 1 | 2022-04-05 00:39 | n-otowa | 2022-04-05 00:39 | n-otowa
149 | 67 | 20192 | 0 | 0 | 1125000 |  |  |  | 2021 |  |  | 1 | 2022-04-05 07:22 | n-otowa
150 | 67 | 20192 | 1 | 0 | 1125000 | 2022-04-05 | 0 |  | 2021 |  |  | 1 | 2022-04-05 07:24 | n-otowa | 2022-04-05 07:24 | n-otowa
151 | 68 | 21783 | 0 | 0 | 18900000 |  |  |  | 2021 |  |  | 1 | 2022-04-06 23:36 | n-otowa
152 | 68 | 21783 | 1 | 0 | 900000 | 2025-03-31 | 0 | 耐震設計は完了。今後の予定として、 2022年度 準備工事（配管、ケーブル類移設） 2023年度 耐震化工事 2024年度 耐震化工事 | 2021 |  |  | 1 | 2022-04-06 23:38 | n-otowa | 2022-04-06 23:38 | n-otowa
153 | 19 | 16513 | 2 | 0 | 152196000 | 2022-07-31 | 0 | 基礎設計変更に伴う工期延長 | 2021 |  |  | 1 | 2022-05-10 01:03 | m-katsurayama | 2022-05-10 04:42 | m-katsurayama
154 | 20 | 19732 | 2 | 0 | 2924000 | 2022-04-30 | 1 | 施工業者の確保が出来ず工期を延長 | 2021 |  |  | 1 | 2022-05-10 01:49 | m-katsurayama | 2022-05-10 04:46 | m-katsurayama
155 | 21 | 21522 | 2 | 0 | 51730000 | 2022-04-30 | 0 | ケーブル新規受注停止による納期延長により繰越 | 2021 |  |  | 1 | 2022-05-10 02:01 | m-katsurayama | 2022-05-10 04:47 | m-katsurayama
156 | 6 | 21877 | 2 | 0 | 9930000 | 2022-07-31 | 1 | 機器納期5ヶ月により繰越 | 2021 |  |  | 1 | 2022-05-10 02:07 | m-katsurayama | 2022-05-10 04:57 | m-katsurayama
157 | 37 | 21902 | 2 | 0 | 2530000 | 2022-05-31 | 1 | 当初計画どおり 継続前提でB号稟議決裁済み | 2021 |  |  | 1 | 2022-05-10 02:08 | m-katsurayama | 2022-05-10 05:04 | m-katsurayama
158 | 50 | 20254 | 2 | 0 | 29620000 | 2022-05-31 | 0 | 生産都合により工事延期 | 2021 |  |  | 1 | 2022-05-10 02:10 | m-katsurayama | 2022-05-10 05:05 | m-katsurayama
159 | 17 | 18304 | 2 | 0 | 387804000 | 2023-02-28 | 0 | 当初の計画通り2023年完工予定 | 2021 |  |  | 1 | 2022-05-10 04:37 | m-katsurayama | 2022-05-10 04:37 | m-katsurayama
160 | 16 | 20824 | 3 | 0 | 55402000 | 2023-03-31 | 0 | 予定工事の一部を除き完了（予定より安価に完了） 引き続き耐震10か年計画に沿って対応する。 | 2021 |  |  | 1 | 2022-05-10 04:38 | m-katsurayama | 2022-05-10 04:38 | m-katsurayama
161 | 68 | 21783 | 2 | 0 | 900000 | 2025-03-31 | 0 | 耐震設計は完了。今後の予定として、 2022年度 準備工事（配管、ケーブル類移設） 2023年度 耐震化工事 2024年度 耐震化工事 | 2021 |  |  | 1 | 2022-05-10 04:39 | m-katsurayama | 2022-05-10 04:39 | m-katsurayama
162 | 15 | 21741 | 3 | 0 | 53600000 | 2022-07-31 | 1 | 当初予定通り7月末完工予定。 ※発注完了状態は「発注完了」としているが、今後の工事で地中障害物が発見、除去が必要な場合は追加予算申請予定。 | 2021 |  |  | 1 | 2022-05-10 04:41 | m-katsurayama | 2022-05-10 04:41 | m-katsurayama
163 | 18 | 16463 | 2 | 0 | 69157000 | 2022-06-30 | 0 | アスベスト含有が確認され工期延長 | 2021 |  |  | 1 | 2022-05-10 04:42 | m-katsurayama | 2022-05-10 04:42 | m-katsurayama
164 | 28 | 21166 | 2 | 0 | 612000 | 2022-04-30 | 1 | 納入されたポンプが仕様と違い、電気工事及び試運転が出来ず繰越 | 2021 |  |  | 1 | 2022-05-10 04:45 | m-katsurayama | 2022-05-10 04:45 | m-katsurayama
165 | 26 | 21358 | 2 | 0 | 2400000 | 2022-04-30 | 1 | 電気配線の整理が必要となり工期延長 | 2021 |  |  | 1 | 2022-05-10 04:46 | m-katsurayama | 2022-05-10 04:46 | m-katsurayama
166 | 22 | 21816 | 2 | 0 | 9842000 | 2022-06-30 | 0 | 製作納期の関係で当初より繰越予定 | 2021 |  |  | 1 | 2022-05-10 04:47 | m-katsurayama | 2022-05-10 04:47 | m-katsurayama
167 | 23 | 21865 | 2 | 0 | 1186000 | 2022-07-31 | 1 | 機器納期4.5ヵ月により繰越 | 2021 |  |  | 1 | 2022-05-10 04:48 | m-katsurayama | 2022-05-10 04:48 | m-katsurayama
168 | 25 | 21896 | 2 | 0 | 8447000 | 2022-06-30 | 0 | 定修で外したファンのFRP/L納期により繰越 | 2021 |  |  | 1 | 2022-05-10 04:48 | m-katsurayama | 2022-05-10 04:48 | m-katsurayama
169 | 4 | 16823 | 2 | 0 | 38240810 | 2022-12-27 | 0 | 当初仕様で予算超過した為、2021定修で内部確認し仕様再検討した | 2021 |  |  | 1 | 2022-05-10 04:53 | m-katsurayama | 2022-05-10 04:53 | m-katsurayama
170 | 2 | 18693 | 2 | 0 | 28292000 | 2022-10-31 | 0 | 2021定修で検査及び補修を行い更新は2022定修とした | 2021 |  |  | 1 | 2022-05-10 04:53 | m-katsurayama | 2022-05-10 04:53 | m-katsurayama
171 | 3 | 21569 | 2 | 0 | 28510000 | 2022-05-31 | 1 | ケーブル新規受注停止による工事・試運転の遅延 | 2021 |  |  | 1 | 2022-05-10 04:54 | m-katsurayama | 2022-05-10 04:54 | m-katsurayama
172 | 5 | 21466 | 2 | 0 | 960000 | 2022-07-31 | 1 | 機器納期5ケ月により繰越 | 2021 |  |  | 1 | 2022-05-10 04:55 | m-katsurayama | 2022-05-10 04:55 | m-katsurayama
173 | 7 | 21292 | 2 | 0 | 9985760 | 2022-09-30 | 1 | 部品納期8ヶ月により繰越 | 2021 |  |  | 1 | 2022-05-10 04:58 | m-katsurayama | 2022-05-10 04:58 | m-katsurayama
174 | 10 | 21464 | 2 | 0 | 3680000 | 2022-11-30 | 1 | 部品納期5ヵ月、8ヶ月により繰越 | 2021 |  |  | 1 | 2022-05-10 04:58 | m-katsurayama | 2022-05-10 04:58 | m-katsurayama
175 | 8 | 21394 | 2 | 0 | 443000 | 2022-06-30 | 1 | 整備期間実働75日により繰越 | 2021 |  |  | 1 | 2022-05-10 04:59 | m-katsurayama | 2022-05-10 04:59 | m-katsurayama
176 | 9 | 21462 | 2 | 0 | 365000 | 2022-05-31 | 1 | 部品納期5ヵ月により繰越 | 2021 |  |  | 1 | 2022-05-10 04:59 | m-katsurayama | 2022-05-10 04:59 | m-katsurayama
177 | 27 | 21262 | 2 | 0 | 586000 | 2022-05-31 | 1 | 機器納期１ヵ年による繰越 | 2021 |  |  | 1 | 2022-05-10 05:00 | m-katsurayama | 2022-05-10 05:00 | m-katsurayama
178 | 12 | 21920 | 2 | 0 | 6395000 | 2022-06-30 | 0 | 年度末発生の追加工事 継続前提でB号稟議決裁済み | 2021 |  |  | 1 | 2022-05-10 05:00 | m-katsurayama | 2022-05-10 05:00 | m-katsurayama
179 | 11 | 21921 | 2 | 0 | 2037000 | 2022-05-31 | 0 | 年度末発生の追加工事 | 2021 |  |  | 1 | 2022-05-10 05:02 | m-katsurayama | 2022-05-10 05:02 | m-katsurayama
180 | 36 | 21276 | 2 | 0 | 4550000 | 2022-09-30 | 1 | ライニング業者の施工ミス | 2021 |  |  | 1 | 2022-05-10 05:02 | m-katsurayama | 2022-05-10 05:02 | m-katsurayama
181 | 65 | 21270 | 2 | 0 | 478000 | 2022-06-30 | 1 | 納期遅延 | 2021 |  |  | 1 | 2022-05-10 05:03 | m-katsurayama | 2022-05-10 05:03 | m-katsurayama
182 | 30 | 18352 | 4 | 0 | 5700000 | 2022-04-28 | 1 | ケーブル配線材の長納期化により繰越しとなる。 | 2021 |  |  | 1 | 2022-05-10 05:04 | m-katsurayama | 2022-05-10 05:04 | m-katsurayama
183 | 31 | 21890 | 3 | 0 | 10200000 | 2022-04-28 | 1 | 機器納入が発注後７カ月となっており、現時点未発注につき納入は７月以降となり繰り越しとなる。 | 2021 |  |  | 1 | 2022-05-10 05:05 | m-katsurayama | 2022-05-10 05:05 | m-katsurayama
184 | 51 | 21176 | 2 | 0 | 5250000 | 2022-12-30 | 0 | 詳細仕様検討中 | 2021 |  |  | 1 | 2022-05-10 05:06 | m-katsurayama | 2022-05-10 05:06 | m-katsurayama
185 | 52 | 20267 | 2 | 0 | 16000000 | 2022-07-31 | 0 | メーカー指導員がコロナ感染し、試運転が延期になったため | 2021 |  |  | 1 | 2022-05-10 05:06 | m-katsurayama | 2022-05-10 05:06 | m-katsurayama
186 | 53 | 20268 | 2 | 0 | 14310000 | 2022-09-30 | 0 | 屋根カバー工法実施前に構造計算を行い健全性を確認した。 然しながらNGとなり建屋補強が必要となったため、追加予算申請予定である。 | 2021 |  |  | 1 | 2022-05-10 05:06 | m-katsurayama | 2022-05-10 05:06 | m-katsurayama
187 | 54 | 20435 | 2 | 0 | 5240000 | 2022-10-31 | 0 | 部品(メカシール)が長納期であったため | 2021 |  |  | 1 | 2022-05-10 05:08 | m-katsurayama | 2022-05-10 05:08 | m-katsurayama
188 | 42 | 20357 | 3 | 0 | 4690000 | 2022-07-31 | 1 | D-367の影響による生産都合 | 2021 |  |  | 1 | 2022-05-10 05:10 | m-katsurayama | 2022-05-10 05:10 | m-katsurayama
189 | 43 | 20347 | 3 | 0 | 1260000 | 2022-05-30 | 1 | D-367の影響による生産都合 | 2021 |  |  | 1 | 2022-05-10 05:11 | m-katsurayama | 2022-05-10 05:11 | m-katsurayama
190 | 66 | 19661 | 2 | 0 | 0 | 2023-03-31 | 1 | 繰越額はゼロであるが入帳不可の為、予算のみ繰越とする。 （入庫上の手続き問題） | 2021 |  |  | 1 | 2022-05-10 05:12 | m-katsurayama | 2022-05-10 05:12 | m-katsurayama
191 | 38 | 21383 | 2 | 0 | 3000000 | 2022-10-31 | 0 | 総合電気室更新工事と工期を合わせるため | 2021 |  |  | 1 | 2022-05-10 05:12 | m-katsurayama | 2022-05-10 05:12 | m-katsurayama
192 | 39 | 21401 | 2 | 0 | 3798000 | 2023-03-31 | 0 | 総合電気室更新工事と工期を合わせるため | 2021 |  |  | 1 | 2022-05-10 05:13 | m-katsurayama | 2022-05-10 05:13 | m-katsurayama
193 | 40 | 21384 | 2 | 0 | 1963000 | 2022-09-30 | 0 | 設計作業が未完のため工事仕様未定 | 2021 |  |  | 1 | 2022-05-10 05:13 | m-katsurayama | 2022-05-10 05:13 | m-katsurayama
194 | 41 | 21755 | 2 | 0 | 3090000 | 2022-10-31 | 0 | 工期が定修期間に限定されるため | 2021 |  |  | 1 | 2022-05-10 05:14 | m-katsurayama | 2022-05-10 05:14 | m-katsurayama
195 | 49 | 21899 | 2 | 0 | 3170000 | 2022-12-31 | 0 | 着手が遅くポンプ未納のため未着工 | 2021 |  |  | 1 | 2022-05-10 05:18 | m-katsurayama | 2022-05-10 05:18 | m-katsurayama
196 | 45 | 21412 | 2 | 0 | 9509000 | 2022-06-30 | 0 | 仕様追加のため | 2021 |  |  | 1 | 2022-05-10 05:20 | m-katsurayama | 2022-05-10 05:20 | m-katsurayama
197 | 46 | 20654 | 2 | 0 | 15600000 | 2022-05-31 | 1 | 原課指示で工期変更 | 2021 |  |  | 1 | 2022-05-10 05:20 | m-katsurayama | 2022-05-10 05:20 | m-katsurayama
198 | 47 | 20648 | 2 | 0 | 960000 | 2022-05-31 | 1 | 分解後軸部の不良が発覚した | 2021 |  |  | 1 | 2022-05-10 05:20 | m-katsurayama | 2022-05-10 05:20 | m-katsurayama
199 | 48 | 20728 | 2 | 0 | 480000 | 2022-05-31 | 1 | 部品納期が04月になったため | 2021 |  |  | 1 | 2022-05-10 05:21 | m-katsurayama | 2022-05-10 05:21 | m-katsurayama
200 | 1 | 17721 | 3 | 0 | 113330000 | 2023-03-31 | 0 | 2021年度削減対象として繰延べ | 2021 |  |  | 1 | 2022-05-10 05:22 | m-katsurayama | 2022-05-10 05:22 | m-katsurayama
201 | 64 | 21917 | 3 | 0 | 4710500 | 2022-09-30 | 0 | 当初計画通りの9月末完工予定。 継続前提でB号稟議決裁済み | 2021 |  |  | 1 | 2022-05-10 05:24 | m-katsurayama | 2022-05-10 05:24 | m-katsurayama
202 | 24 | 21873 | 2 | 0 | 1635000 | 2022-05-31 | 1 | 長納期の為、当初予定通り 継続前提でB号稟議決裁済み | 2021 |  |  | 1 | 2022-05-10 05:25 | m-katsurayama | 2022-05-10 05:25 | m-katsurayama
203 | 14 | 20012 | 4 | 0 | 414970000 | 2022-08-31 | 0 | 当初の予定通り、2022年8月に完工予定。 | 2021 |  |  | 1 | 2022-05-10 05:26 | m-katsurayama | 2022-05-10 05:26 | m-katsurayama
204 | 56 | 18003 | 2 | 0 | 8060000 | 2022-12-30 | 0 | 新規蒸気ヘッダー図面作成に必要な現地調査、熱応力解析に時間を要するため | 2021 |  |  | 1 | 2022-05-10 05:27 | m-katsurayama | 2022-05-10 05:27 | m-katsurayama
205 | 55 | 20720 | 2 | 0 | 62890000 | 2022-08-31 | 0 | コンプレッサー納期遅延および工事見積遅延のため | 2021 |  |  | 1 | 2022-05-10 05:28 | m-katsurayama | 2022-05-10 05:28 | m-katsurayama
206 | 57 | 20734 | 3 | 0 | 25082000 | 2022-05-31 | 0 | 基礎撤去工事が発生した | 2021 |  |  | 1 | 2022-05-10 05:28 | m-katsurayama | 2022-05-10 05:28 | m-katsurayama
207 | 59 | 19869 | 3 | 0 | 10499000 | 2022-08-31 | 0 | 材料長納期およびMM-1行蒸気配管の改造に時間を要するため | 2021 |  |  | 1 | 2022-05-10 05:30 | m-katsurayama | 2022-05-10 05:30 | m-katsurayama
208 | 58 | 21911 | 2 | 0 | 1055000 | 2022-05-31 | 0 | フレキホース追加購入および追加工事発生 | 2021 |  |  | 1 | 2022-05-10 05:31 | m-katsurayama | 2022-05-10 05:31 | m-katsurayama
209 | 63 | 21927 | 2 | 0 | 27000000 | 2022-07-31 | 0 | 工期に時間を要するため 継続前提でA号稟議決裁済み | 2021 |  |  | 1 | 2022-05-10 05:32 | m-katsurayama | 2022-05-10 05:32 | m-katsurayama
210 | 61 | 21667 | 2 | 0 | 1900000 | 2022-09-30 | 1 | 長納期のため | 2021 |  |  | 1 | 2022-05-10 05:33 | m-katsurayama | 2022-05-10 05:33 | m-katsurayama
211 | 62 | 21417 | 2 | 0 | 2385000 | 2022-06-30 | 0 | 1321YY641工事が完了後に着工可能となるため | 2021 |  |  | 1 | 2022-05-10 05:34 | m-katsurayama | 2022-05-10 05:34 | m-katsurayama
212 | 60 | 20612 | 2 | 0 | 6000000 | 2022-04-30 | 1 | 足場撤去が期間内に完工しなかったため | 2021 |  |  | 1 | 2022-05-10 05:34 | m-katsurayama | 2022-05-10 05:34 | m-katsurayama
213 | 33 | 21695 | 2 | 0 | 2836795 | 2022-06-30 | 0 | 次年度も引き続きシステム開発を行う為。 | 2021 |  |  | 1 | 2022-05-10 05:37 | m-katsurayama | 2022-05-10 05:37 | m-katsurayama
214 | 29 | 19995 | 2 | 0 | 6150000 | 2022-05-31 | 1 | 急遽試掘作業が発生し、構造計算期間がズレ込んだ為、繰り越しが必要となった。 | 2021 |  |  | 1 | 2022-05-10 05:37 | m-katsurayama | 2022-05-10 05:37 | m-katsurayama
215 | 32 | 21791 | 2 | 0 | 1600000 | 2022-05-31 | 1 | A工場静置建屋東側ﾊﾟｲﾌﾟﾗｯｸ補強関係で追加工事が発生した為、繰越とする。 | 2021 |  |  | 1 | 2022-05-10 05:38 | m-katsurayama | 2022-05-10 05:38 | m-katsurayama
216 | 34 | 20630 | 2 | 0 | 19791000 | 2023-03-31 | 0 | OPCサーバーからPIサーバーに接続する為のOPCサーバーアップグレードが2022年1月中旬まで伸びてしまい繰越となった。 | 2021 |  |  | 1 | 2022-05-10 05:39 | m-katsurayama | 2022-05-10 05:39 | m-katsurayama
217 | 35 | 20169 | 2 | 0 | 25559200 | 2022-05-31 | 0 | 電気部品遅延による消防検査未受検、消防検査後に実施される付帯設備の改造（仕様書発行済み）がある為、繰越とする。※完工予定月は５月末としているが未だ納期情報入らず。 | 2021 |  |  | 1 | 2022-05-10 05:40 | m-katsurayama | 2022-05-10 05:40 | m-katsurayama
218 | 13 | 21670 | 2 | 0 | 365000 | 2022-06-30 | 1 | 製品品質に問題があり、原課より問題解決までストップが掛かり工事実施待ち状態となっている。（発注済み） | 2021 |  |  | 1 | 2022-05-10 05:41 | m-katsurayama | 2022-05-10 05:41 | m-katsurayama
219 | 17 | 18304 | 3 | 0 | 387804000 | 2023-02-28 | 0 | 当初の計画通り2023年完工予定 | 2021 | 2022 | E22A1021 | 0 | 2022-05-10 05:48 | m-katsurayama | 2022-05-10 05:48 | m-katsurayama
220 | 16 | 20824 | 4 | 0 | 55402000 | 2023-03-31 | 0 | 予定工事の一部を除き完了（予定より安価に完了） 引き続き耐震10か年計画に沿って対応する。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-10 05:49 | m-katsurayama | 2022-05-10 05:49 | m-katsurayama
221 | 15 | 21741 | 4 | 0 | 53600000 | 2022-07-31 | 0 | 当初予定通り7月末完工予定。 ※発注完了状態は「発注完了」としているが、今後の工事で地中障害物が発見、除去が必要な場合は追加予算申請予定。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-10 05:51 | m-katsurayama | 2022-05-10 05:51 | m-katsurayama
222 | 68 | 21783 | 3 | 0 | 900000 | 2025-03-31 | 0 | 耐震設計は完了。今後の予定として、 2022年度 準備工事（配管、ケーブル類移設） 2023年度 耐震化工事 2024年度 耐震化工事 | 2021 | 2022 | E22A1021 | 0 | 2022-05-10 05:52 | m-katsurayama | 2022-05-10 05:52 | m-katsurayama
223 | 19 | 16513 | 3 | 0 | 152196000 | 2022-07-31 | 0 | 基礎設計変更に伴う工期延長 | 2021 | 2022 | E22A1021 | 0 | 2022-05-11 06:00 | m-katsurayama | 2022-05-11 06:00 | m-katsurayama
224 | 18 | 16463 | 3 | 0 | 69157000 | 2022-06-30 | 0 | アスベスト含有が確認され工期延長 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:24 | m-katsurayama | 2022-05-13 01:24 | m-katsurayama
225 | 28 | 21166 | 3 | 0 | 612000 | 2022-04-30 | 1 | 納入されたポンプが仕様と違い、電気工事及び試運転が出来ず繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:26 | m-katsurayama | 2022-05-13 01:26 | m-katsurayama
226 | 26 | 21358 | 3 | 0 | 2400000 | 2022-04-30 | 1 | 電気配線の整理が必要となり工期延長 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:26 | m-katsurayama | 2022-05-13 01:26 | m-katsurayama
227 | 20 | 19732 | 3 | 0 | 2924000 | 2022-04-30 | 1 | 施工業者の確保が出来ず工期を延長 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:27 | m-katsurayama | 2022-05-13 01:27 | m-katsurayama
228 | 21 | 21522 | 3 | 0 | 51730000 | 2022-04-30 | 0 | ケーブル新規受注停止による納期延長により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:27 | m-katsurayama | 2022-05-13 01:27 | m-katsurayama
229 | 22 | 21816 | 3 | 0 | 9842000 | 2022-06-30 | 0 | 製作納期の関係で当初より繰越予定 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:28 | m-katsurayama | 2022-05-13 01:28 | m-katsurayama
230 | 23 | 21865 | 3 | 0 | 1186000 | 2022-07-31 | 1 | 機器納期4.5ヵ月により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:32 | m-katsurayama | 2022-05-13 01:32 | m-katsurayama
231 | 25 | 21896 | 3 | 0 | 8447000 | 2022-06-30 | 0 | 定修で外したファンのFRP/L納期により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:32 | m-katsurayama | 2022-05-13 01:32 | m-katsurayama
232 | 3 | 21569 | 3 | 0 | 28510000 | 2022-05-31 | 1 | ケーブル新規受注停止による工事・試運転の遅延 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:41 | m-katsurayama | 2022-05-13 01:41 | m-katsurayama
233 | 2 | 18693 | 3 | 0 | 28292000 | 2022-10-31 | 0 | 2021定修で検査及び補修を行い更新は2022定修とした | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:42 | m-katsurayama | 2022-05-13 01:42 | m-katsurayama
234 | 4 | 16823 | 3 | 0 | 38240810 | 2022-12-27 | 0 | 当初仕様で予算超過した為、2021定修で内部確認し仕様再検討した | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:42 | m-katsurayama | 2022-05-13 01:42 | m-katsurayama
235 | 5 | 21466 | 3 | 0 | 960000 | 2022-07-31 | 1 | 機器納期5ケ月により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:43 | m-katsurayama | 2022-05-13 01:43 | m-katsurayama
236 | 6 | 21877 | 3 | 0 | 9930000 | 2022-07-31 | 1 | 機器納期5ヶ月により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:43 | m-katsurayama | 2022-05-13 01:43 | m-katsurayama
237 | 7 | 21292 | 3 | 0 | 9985760 | 2022-09-30 | 1 | 部品納期8ヶ月により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:44 | m-katsurayama | 2022-05-13 01:44 | m-katsurayama
238 | 10 | 21464 | 3 | 0 | 3680000 | 2022-11-30 | 1 | 部品納期5ヵ月、8ヶ月により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:45 | m-katsurayama | 2022-05-13 01:45 | m-katsurayama
239 | 8 | 21394 | 3 | 0 | 443000 | 2022-06-30 | 1 | 整備期間実働75日により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:46 | m-katsurayama | 2022-05-13 01:46 | m-katsurayama
240 | 9 | 21462 | 3 | 0 | 365000 | 2022-05-31 | 1 | 部品納期5ヵ月により繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:46 | m-katsurayama | 2022-05-13 01:46 | m-katsurayama
241 | 27 | 21262 | 3 | 0 | 586000 | 2022-05-31 | 1 | 機器納期１ヵ年による繰越 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:47 | m-katsurayama | 2022-05-13 01:47 | m-katsurayama
242 | 12 | 21920 | 3 | 0 | 6395000 | 2022-06-30 | 0 | 年度末発生の追加工事 継続前提でB号稟議決裁済み | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:47 | m-katsurayama | 2022-05-13 01:47 | m-katsurayama
243 | 11 | 21921 | 3 | 0 | 2037000 | 2022-05-31 | 0 | 年度末発生の追加工事 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:47 | m-katsurayama | 2022-05-13 01:47 | m-katsurayama
244 | 36 | 21276 | 3 | 0 | 4550000 | 2022-09-30 | 1 | ライニング業者の施工ミス | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:48 | m-katsurayama | 2022-05-13 01:48 | m-katsurayama
245 | 65 | 21270 | 3 | 0 | 478000 | 2022-06-30 | 1 | 納期遅延 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:48 | m-katsurayama | 2022-05-13 01:48 | m-katsurayama
246 | 37 | 21902 | 3 | 0 | 2530000 | 2022-05-31 | 1 | 当初計画どおり 継続前提でB号稟議決裁済み | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:49 | m-katsurayama | 2022-05-13 01:49 | m-katsurayama
247 | 30 | 18352 | 5 | 0 | 5700000 | 2022-04-28 | 1 | ケーブル配線材の長納期化により繰越しとなる。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:50 | m-katsurayama | 2022-05-13 01:50 | m-katsurayama
248 | 31 | 21890 | 4 | 0 | 10200000 | 2022-04-28 | 1 | 機器納入が発注後７カ月となっており、現時点未発注につき納入は７月以降となり繰り越しとなる。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:50 | m-katsurayama | 2022-05-13 01:50 | m-katsurayama
249 | 50 | 20254 | 3 | 0 | 29620000 | 2022-05-31 | 0 | 生産都合により工事延期 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:51 | m-katsurayama | 2022-05-13 01:51 | m-katsurayama
250 | 51 | 21176 | 3 | 0 | 5250000 | 2022-12-30 | 0 | 詳細仕様検討中 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:52 | m-katsurayama | 2022-05-13 01:52 | m-katsurayama
251 | 52 | 20267 | 3 | 0 | 16000000 | 2022-07-31 | 0 | メーカー指導員がコロナ感染し、試運転が延期になったため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:52 | m-katsurayama | 2022-05-13 01:52 | m-katsurayama
252 | 53 | 20268 | 3 | 0 | 14310000 | 2022-09-30 | 0 | 屋根カバー工法実施前に構造計算を行い健全性を確認した。 然しながらNGとなり建屋補強が必要となったため、追加予算申請予定である。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:53 | m-katsurayama | 2022-05-13 01:53 | m-katsurayama
253 | 54 | 20435 | 3 | 0 | 5240000 | 2022-10-31 | 0 | 部品(メカシール)が長納期であったため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:53 | m-katsurayama | 2022-05-13 01:53 | m-katsurayama
254 | 42 | 20357 | 4 | 0 | 4690000 | 2022-07-31 | 1 | D-367の影響による生産都合 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:55 | m-katsurayama | 2022-05-13 01:55 | m-katsurayama
255 | 43 | 20347 | 4 | 0 | 1260000 | 2022-05-30 | 1 | D-367の影響による生産都合 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 01:56 | m-katsurayama | 2022-05-13 01:56 | m-katsurayama
256 | 66 | 19661 | 3 | 0 | 0 | 2023-03-31 | 1 | 繰越額はゼロであるが入帳不可の為、予算のみ繰越とする。 （入庫上の手続き問題） | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:14 | m-katsurayama | 2022-05-13 02:14 | m-katsurayama
257 | 38 | 21383 | 3 | 0 | 3000000 | 2022-10-31 | 0 | 総合電気室更新工事と工期を合わせるため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:24 | m-katsurayama | 2022-05-13 02:24 | m-katsurayama
258 | 39 | 21401 | 3 | 0 | 3798000 | 2023-03-31 | 0 | 総合電気室更新工事と工期を合わせるため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:24 | m-katsurayama | 2022-05-13 02:24 | m-katsurayama
259 | 40 | 21384 | 3 | 0 | 1963000 | 2022-09-30 | 0 | 設計作業が未完のため工事仕様未定 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:25 | m-katsurayama | 2022-05-13 02:25 | m-katsurayama
260 | 41 | 21755 | 3 | 0 | 3090000 | 2022-10-31 | 0 | 工期が定修期間に限定されるため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:25 | m-katsurayama | 2022-05-13 02:25 | m-katsurayama
261 | 44 | 21793 | 5 | 0 | 18260000 | 2022-12-31 | 0 | 定修に工期変更(仕様追加実施時期） 継続前提でA号稟議決裁済み | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:26 | m-katsurayama | 2022-05-13 02:26 | m-katsurayama
262 | 49 | 21899 | 3 | 0 | 3170000 | 2022-12-31 | 0 | 着手が遅くポンプ未納のため未着工 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:26 | m-katsurayama | 2022-05-13 02:26 | m-katsurayama
263 | 45 | 21412 | 3 | 0 | 9509000 | 2022-06-30 | 0 | 仕様追加のため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:27 | m-katsurayama | 2022-05-13 02:27 | m-katsurayama
264 | 46 | 20654 | 3 | 0 | 15600000 | 2022-05-31 | 1 | 原課指示で工期変更 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:27 | m-katsurayama | 2022-05-13 02:27 | m-katsurayama
265 | 47 | 20648 | 3 | 0 | 960000 | 2022-05-31 | 1 | 分解後軸部の不良が発覚した | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:28 | m-katsurayama | 2022-05-13 02:28 | m-katsurayama
266 | 48 | 20728 | 3 | 0 | 480000 | 2022-05-31 | 1 | 部品納期が04月になったため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:28 | m-katsurayama | 2022-05-13 02:28 | m-katsurayama
267 | 1 | 17721 | 4 | 0 | 113330000 | 2023-03-31 | 0 | 2021年度削減対象として繰延べ | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:29 | m-katsurayama | 2022-05-13 02:29 | m-katsurayama
268 | 64 | 21917 | 4 | 0 | 4710500 | 2022-09-30 | 0 | 当初計画通りの9月末完工予定。 継続前提でB号稟議決裁済み | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:30 | m-katsurayama | 2022-05-13 02:30 | m-katsurayama
269 | 24 | 21873 | 3 | 0 | 1635000 | 2022-05-31 | 1 | 長納期の為、当初予定通り 継続前提でB号稟議決裁済み | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:31 | m-katsurayama | 2022-05-13 02:31 | m-katsurayama
270 | 14 | 20012 | 5 | 0 | 414970000 | 2022-08-31 | 0 | 当初の予定通り、2022年8月に完工予定。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:31 | m-katsurayama | 2022-05-13 02:31 | m-katsurayama
271 | 13 | 21670 | 3 | 0 | 365000 | 2022-06-30 | 1 | 製品品質に問題があり、原課より問題解決までストップが掛かり工事実施待ち状態となっている。（発注済み） | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:32 | m-katsurayama | 2022-05-13 02:32 | m-katsurayama
272 | 61 | 21667 | 3 | 0 | 1900000 | 2022-09-30 | 1 | 長納期のため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:32 | m-katsurayama | 2022-05-13 02:32 | m-katsurayama
273 | 62 | 21417 | 3 | 0 | 2385000 | 2022-06-30 | 0 | 1321YY641工事が完了後に着工可能となるため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:33 | m-katsurayama | 2022-05-13 02:33 | m-katsurayama
274 | 60 | 20612 | 3 | 0 | 6000000 | 2022-04-30 | 1 | 足場撤去が期間内に完工しなかったため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:33 | m-katsurayama | 2022-05-13 02:33 | m-katsurayama
275 | 56 | 18003 | 3 | 0 | 8060000 | 2022-12-30 | 0 | 新規蒸気ヘッダー図面作成に必要な現地調査、熱応力解析に時間を要するため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:34 | m-katsurayama | 2022-05-13 02:34 | m-katsurayama
276 | 55 | 20720 | 3 | 0 | 62890000 | 2022-08-31 | 0 | コンプレッサー納期遅延および工事見積遅延のため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:35 | m-katsurayama | 2022-05-13 02:35 | m-katsurayama
277 | 57 | 20734 | 4 | 0 | 25082000 | 2022-05-31 | 0 | 基礎撤去工事が発生した | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:35 | m-katsurayama | 2022-05-13 02:35 | m-katsurayama
278 | 59 | 19869 | 4 | 0 | 10499000 | 2022-08-31 | 0 | 材料長納期およびMM-1行蒸気配管の改造に時間を要するため | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:35 | m-katsurayama | 2022-05-13 02:35 | m-katsurayama
279 | 58 | 21911 | 3 | 0 | 1055000 | 2022-05-31 | 0 | フレキホース追加購入および追加工事発生 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:36 | m-katsurayama | 2022-05-13 02:36 | m-katsurayama
280 | 63 | 21927 | 3 | 0 | 27000000 | 2022-07-31 | 0 | 工期に時間を要するため 継続前提でA号稟議決裁済み | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:37 | m-katsurayama | 2022-05-13 02:37 | m-katsurayama
281 | 33 | 21695 | 3 | 0 | 2836795 | 2022-06-30 | 0 | 次年度も引き続きシステム開発を行う為。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:37 | m-katsurayama | 2022-05-13 02:37 | m-katsurayama
282 | 29 | 19995 | 3 | 0 | 6150000 | 2022-05-31 | 0 | 急遽試掘作業が発生し、構造計算期間がズレ込んだ為、繰り越しが必要となった。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:38 | m-katsurayama | 2022-05-13 02:38 | m-katsurayama
283 | 32 | 21791 | 3 | 0 | 1600000 | 2022-05-31 | 1 | A工場静置建屋東側ﾊﾟｲﾌﾟﾗｯｸ補強関係で追加工事が発生した為、繰越とする。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:39 | m-katsurayama | 2022-05-13 02:39 | m-katsurayama
284 | 34 | 20630 | 3 | 0 | 19791000 | 2023-03-31 | 0 | OPCサーバーからPIサーバーに接続する為のOPCサーバーアップグレードが2022年1月中旬まで伸びてしまい繰越となった。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:39 | m-katsurayama | 2022-05-13 02:39 | m-katsurayama
285 | 35 | 20169 | 3 | 0 | 25559200 | 2022-05-31 | 0 | 電気部品遅延による消防検査未受検、消防検査後に実施される付帯設備の改造（仕様書発行済み）がある為、繰越とする。※完工予定月は５月末としているが未だ納期情報入らず。 | 2021 | 2022 | E22A1021 | 0 | 2022-05-13 02:39 | m-katsurayama | 2022-05-13 02:39 | m-katsurayama